## Tasks
Learning ZAX — Book Improvement Issue Tracker
ID | Priority | Type | File / Chapter | Issue Description | Specific Action Required | Status | Est. Effort | Session Notes
T01 | High | New content | README.md (root) | No front door: book begins with a table of contents. A complete beginner never learns why they should care about assembly, why the Z80, or what they'll be able to do. | Write a 1-page introduction: what assembly is for; why the Z80 is a good learning machine; what the reader will be able to build by the end. Add to root README or as a new INTRODUCTION.md. | Not started | S (0.5 hr)
T02 | High | Structural | part1/01-the-computer.md | Chapter 1 has no code. Reader absorbs the full flags register table, 17 registers, hex conversion, and endianness before writing a single instruction — no reason to care yet. | Defer the full flags register table to Appendix 2 (where it already lives). Add one motivating machine-code byte example early in the chapter. Move endianness closer to where it is first needed (Ch 2). | Not started | M (1 hr)
T03 | High | Structural | part1/03-assembly-language.md | Chapter 3 introduces LD (12 forms + summary table), sections, named storage, constants, ADD/INC/DEC, and signed/unsigned values in one sitting. Two's complement appears here but isn't used until Ch 4. | Split into Ch 3 (LD basics: reg-reg, immediate, (HL) indirect, named storage, parentheses rule) and Ch 3b or Ch 4-prelude (LD advanced forms + two's complement, moved to Ch 4 where signed arithmetic is needed). | Done | L (2 hr)
T04 | High | Prose | part1/03-assembly-language.md | 'Parentheses always mean memory' is the single most important rule in the chapter but is buried in a section header. Beginners get this wrong constantly. | Promote this rule to a visually distinct callout block (bold/boxed) immediately after the first example that uses parentheses. Repeat it as a one-liner summary in the chapter Summary section. | Done | S (0.5 hr)
T05 | High | New content | part1/04-flags-comparisons-jumps.md | The book identifies flag tracking as hard but gives no method. The reader is told to track flags carefully with no tools for doing so. | Add a named 'flag-before-branch' technique box in Ch 4: when you write a conditional jump, ask (1) which instruction last set the flag? (2) does anything between that instruction and the jump also set it? Make this a named concept referenced by name in later chapters. | Done | M (1 hr)
T06 | High | New content | part1/10-functions-and-the-ix-frame.md | The (ix+name+0) and (ix+name+1) byte-lane notation is explained in one paragraph. Without a picture of the stack frame layout, the reader is memorising syntax without understanding the mechanism. | Add an ASCII or table diagram showing a concrete stack frame: for a func with two parameters (addr, byte), show SP, IX, and each slot in memory with exact offsets. Label which (ix+name+0/1) expression reads which byte. | Not started | M (1 hr)
T07 | High | New content | part1/ (all chapters 3–13) | Part 1 has zero exercises. Part 2 has four per chapter. Beginners learning assembly must write code; reading alone doesn't build the skill. | Write 3–4 exercises per chapter for Part 1 chapters 3–13. Exercises should range from simple modifications (change a loop count, add a variable) to 'what if' questions about flag behaviour and correctness. | Done | XL (5 hr) | Highest-impact single gap. Do Ch 3, 4, 5 first.
T08 | High | New content | part1/ (new section or file) | No debugging guidance anywhere in the book. If a beginner's program gives wrong output, they have no framework for finding out why. | Add a 'When Things Go Wrong' section — either at the end of Ch 3 (first runnable program) or as a standalone short chapter. Cover: compile and inspect the assembler listing; use the emulator's step/trace mode; check register state after each call; trace flag state by hand with a table. | Done | M (1.5 hr) | Could also be an appendix.
T09 | High | New content | part1/03-assembly-language.md or README | The boundary between raw Z80 and ZAX additions is never explicitly stated. Readers who search for 'func' or 'if NZ' in Z80 references won't find them and won't know why. | Add a short 'What ZAX adds' explainer (half a page): list the Z80 instructions vs the ZAX constructs (func, if/while/select, :=, step, op, var, section, const) and explain that ZAX compiles to Z80 with no hidden runtime. | Done | S (0.5 hr) | Natural home: after first ZAX-specific syntax in Ch 3.
T10 | Medium | Prose | part1/01-the-computer.md | Hex and binary conversion tables appear before the reader has any reason to care about them. The 'why' is missing. | Add one or two sentences before the positional-value table explaining when programmers actually need to convert: reading memory dumps, checking a status byte's individual bits, verifying an address is in the right range. | Done | S (0.5 hr)
T11 | Medium | Prose | part1/09-a-phase-a-program.md | The push/pop in count_above that 'does no useful work' is presented as raw-Z80 friction, but an experienced programmer would just write ld d, 0 directly. The example slightly constructs the problem. | Revise the explanation: acknowledge that ld d, 0 is mechanically safe here, but explain that in a larger function with more registers active, proving safety requires careful reading of every instruction in scope — and that this discipline becomes the burden. | Done | S (0.5 hr)
T12 | Medium | Structural | part2/00-introduction.md + part2/01-foundations.md | Part 2 re-explains :=, func, and while NZ in detail for readers who just completed Part 1. This is redundant for that audience and inconsistently done. | Keep the re-introduction in Part 2 Ch 1 (for the 'prior Z80 experience' audience) but add a note: 'If you completed Part 1, the material in this section is familiar — skip to The Chapter 01 Programs.' Trim the flag-establishment re-explanations to a one-line reminder. | Done | S (0.5 hr)
T13 | Medium | Structural | part2/09-gaps-and-futures.md | The final chapter of the course ends on a list of language limitations. After a demanding course, this is deflating. | Move the full friction log to docs/design/ or an appendix. Retain a short paragraph in Ch 9 summarising what was resolved (break/continue) vs what remains open. End the chapter with a forward-looking close: what the reader can build now, where to go next. | Done | M (1 hr)
T14 | Medium | Prose | part1/ (all chapters) | 'flag-before-branch' pattern is re-explained 8+ times across Part 1 and Part 2. After T05 names it, later occurrences should reference the name rather than repeat the explanation. | After T05 is done: do a pass through all Part 1 chapters and replace full re-explanations of the or-a flag-establishment pattern with a brief '(flag-before-branch pattern from Ch 4)' callout. | Done | M (1 hr) | Depends on T05.
T15 | Medium | Prose | part1/08-io-and-ports.md | Interrupts are completely absent. Hardware programmers will need them almost immediately after finishing the course. | Add a paragraph at the end of Ch 8 or in an appendix: 'This course covers polled I/O. The Z80 also supports interrupt-driven I/O via EI/DI and interrupt modes 0/1/2, which are beyond this course's scope. [Reference to further reading].' | Done | S (0.5 hr)
T16 | Medium | Prose | part2/ (all chapters) | Part 2 prose is good but inconsistent in places: some sections re-explain flag establishment at length, others assume the reader knows it; some chapters use the full ld a, 1/or a idiom without comment. | Prose pass over Part 2: trim re-explanations that duplicate Part 1, ensure consistent tone, and replace verbose idiom explanations with named-technique references after T14 is done. | Done | L (2 hr) | Do after T14.
T17 | Medium | Prose | part1/07-stack-and-subroutines.md | The distinction between a ZAX func block and a raw labeled subroutine (the ret requirement difference) is made but could be more prominent. | Add a callout box or short 'ZAX func vs raw subroutine' comparison table: when you use each, what the compiler generates, why ret is required in one and optional in the other. | Done | S (0.5 hr)
T18 | Low | Review | appendices/ (all) | After the structural changes in T02 and T03, the appendices should be checked: the flags table and register table may now be the first place certain content appears. | After T02 and T03 are complete, review the four appendices: ensure they are cross-referenced correctly from the revised chapters and that no content has been duplicated or orphaned. | Done | S (0.5 hr) | Depends on T02, T03.
T19 | Low | Prose | part1/ (all chapters) | General prose quality pass: sentence rhythm, redundant hedging phrases, passive-voice overuse, and the occasional place where the writing drifts into reference-manual style. | Full prose quality pass over Part 1 chapters 1–13. Focus on: opening paragraphs of each chapter (set the purpose clearly), transitions between sections, and Summary sections (currently excellent — maintain this standard). | Done | XL (4 hr) | Do last, after all structural changes.
T20 | Low | New content | part1/ (README or intro) | The book has no statement of what system the examples run on, what emulator to use, or what 'platform-agnostic' means in practice. The TEC-1 is mentioned once in passing. | Add a 'Hardware and emulator setup' section to the Part 1 README or root README: name the target system (or explain the platform-agnostic approach), link to the emulator, and show how to verify that a compiled program ran correctly. | Done | S (0.5 hr)

## Summary
Book Improvement — Summary Dashboard
By Priority | 9 | 3 | 6
High | 8 | 0 | 8
Medium | 3 | 0 | 3
Low | 20 | 3 | 17
TOTAL
By Type | Total Tasks | Not Started | Done
New content
Structural
Prose
Review
Effort Key | Approx. Time
S (small) | ~30 min
M (medium) | ~1 hr
L (large) | ~2 hr
XL (x-large) | 4–5 hr